## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | (Fill your Project Number here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
PROJECT NUMBER | 46
PROJECT NAME | Color Auto Correction in Wedding Photographs
PROJECT MENTOR (sponsor) | Jaya Bharadwaj)
First Client meet was done on 2nd february (after a new client was assigned on 31st January)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Mahesh | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | John | 1 | 1.5 | Ongoing |  | -0.5 | 33.3333
Client meeting | Coordination | Kavya | 5 |  | Planned | Make sure scoping questions are included
Get account and configure website | Preparation | Archana | 1.5 | 1 | Done |  | 0.5 | 50
Research existing technology | Preparation | Mahesh | 2 | 1.5 | Ongoing |  | 0.5 | 33.3333
Project synopsis writeup | Documentation | Archana | 2 |  | Planned
Identify role owners | Preparation | Mahesh | 1 | 0.6 | Done | Multiple roles are OK - think about role & reponsibility distribution | 0.4 | 66.6667
Team Meeting | Coordination | John | 1 | 2 | Done |  | -1 | 50
Status tracker | Documentation | Seth | 1 |  | Planned
Week 2 (January 22 - January 28)
Learn Eclipse | Preparation | Elliot | 4 |  | Planned | Using IDEs can make our job easier
GIT Repository setup | Preparation | John | 1 |  | Planned
Discuss bug report software | Preparation | Seth | 1.5 |  | Planned | This is critical to project success
Develop questions for requirements elicitation | Documentation | Kavya | 5 |  | Planned | Make sure scoping questions are included
Get account and configure website | Preparation | Archana | 1.5 |  | Planned
Team Meeting | Coordination | John | 1 |  | Planned
Status tracker | Documentation | Seth | 1 |  | Planned
Week 4(6 Feb-12 Feb)
Fix meeting with client | Requirements | Sujal | 0.75 | 0.5 | Done |  | 0.25 | 50
GIT Repository setup | Preparation | Abhinav,Harsh | 5 | 6 | Done |  | -1 | 16.6667
Client meeting | Preparation | Full Team | 1 | 1.5 | Done |  | -0.5 | 33.3333
Research existing technology
Project synopsis writeup | Preparation | Deekshitha | 1 | 0.75 | Done |  | 0.25 | 33.3333
Team Meeting | Requirements | Full Team | 1 | 1.5 | Done |  | -0.5 | 33.3333
Status tracker | Documentation | Ishan | 1 | 0.75 | Done |  | 0.25 | 33.3333
Week 5(12 Feb-19 Feb)
Client Meet | Requirements | Full Team | 0.5 | 1.5 | Done |  | -1 | 66.6667
Project Plan | Documentation | Harsh, Abhinav | 2 | 2 | Done
Contact Photographers | Requirements | Sujal | 6 |  | Ongoing | There are over 100 photographers that need to be contacted and each one has their own preferred timings
Collect datasets | Requirements | Sujal | 2 | 2.5 | Done |  | -0.5 | 20
Final Papers and Research | Requirements | Harsh, Ishan | 6 | 5 | Done |  | 1 | 20
Research Existing Tools | Requirements | Abhinav | 4 | 4.5 | Done |  | -0.5 | 11.1111
See implementation of Libraries | Requirements | Deekshitha | 4 | 3.5 | Done |  | 0.5 | 14.2857
Fix meeting with client | Requirements | Sujal | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Ishan | 0.5 | 0.5 | Done |  | 0 | 0
Create UI | Interfaces | Full Team | 10 |  | Ongoing
SRS Document | Documentation | Deekshitha, Abhinav, Sujal | 3 | 3 | Done
Team Meeting | Preparation | Full Team | 1 | 1.5 | Done
Week 6(19 Feb- 25 Feb)
Client meeting | Requirements | Full Team | 1 | 1.5 | Done |  | -0.5 | 33.3333
Test Plan | Requirements | Harsh, Ishan | 2 | 2 | Done |  | 0 | 0
Team Meeting | Design | Full Team | 2 | 1 | Done
Status tracker | Documentation | Ishan | 0.5 | 0.5 | Done |  | 0 | 0
Edit images in a folder | Development | Abhinav | 2 | 1 | Done
Coding Session | Development | Full Team | 2 | 1.5 | Done |  | 0.5 | 33.3333
Fix meeting with client | Requirements | Sujal | 0.5 | 0.5 | Done |  | 0 | 0
MOM | Documentation | Sujal | 0.5 | 0.5 | Done
Make list of studios in Kondapur | Requirements | Sujal, Deekshitha | 1 | 1 | Done |  | 0 | 0
Week 7(25 Feb- 3Mar)
Team Meeting | Design | Full Team | 1 |  | Done
Coding Session | Development | Full Team | 4 |  | Done
Research Pytorch | Preparation | Harsh,Ishan | 5 |  | Done
Status Tracker | Documentation | Ishan | 0.5 |  | Delayed | Midsem week
Research | Preparation | Deekshitha, Abhinav, Sujal | 6 |  | Done
Contact people in CVIT | Coordination | Abhinav | 1 |  | Done
Week 8(4 Mar- 10Mar)
Train regression models | Development | Abhinav | 4 |  | Ongoing
Train Resnet 18 | Development | Ishan | 4 | 5 | Done |  | -1 | 20
Train Resnet 50 | Development | Harsh | 4.5 |  | Ongoing
Fix meeting with client | Coordination | Sujal | 0.5 |  | Done
Create basic UI | Development | Sujal | 3 |  | Ongoing
Train EnlightenGAN | Development | Deekshitha | 5 |  | Ongoing
Week 9(11Mar- 17Mar)
Client meeting | Coordination | Full Team | 1.5 |  | Planned
Note on C6: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G6: swami: Insert your own comments
Note on H6: SE: This field is updated automatically